## Slide 1
JULY 2026 · NS-3 ENHANCEMENT PROGRESS
Traffic QoS Model & Switch Reliability
3-flow robot traffic · BSSID crash fix · recovery measurement · seed matrix
Robot NW Connection Simulator · Hybrid WiFi Mesh + 5G NR / LTE

## Slide 2
OVERVIEW
What this update covers
01
July deliverable
3-flow QoS traffic model (Control / Sensor / Video) + per-flow metrics
02
Crash fix
WiFi BSSID assert during multi-AP roaming — root cause & patch
03
Recovery logic
Switch resolution improved from ~57% → ~80%+ on representative runs
04
Seed differences
Full 3×3 matrix (seeds 6/7/8 × STA 5/10/15) — why one seed is not enough
05
Alignment
July plan checklist vs current status
06
Next
192-run campaign to produce the proper analysis report
Robot NW Connection Simulator · July 2026 Progress
2 / 8

## Slide 3
JULY DELIVERABLE
Per-flow QoS traffic model
Replaced generic HTTP/VoIP mix with robot-realistic 3-flow model + DSCP marking.
Control
UDP · EF
~1 KB / 50 ms
Target: ≤ 50 ms · 0% loss
Sensor
TCP · AF31
100 KB / 200 ms
Target: ≤ 200 ms · < 5% loss
Video
TCP · AF41
5 Mbps continuous
Target: ≤ 500 ms · < 10% loss
Artifacts delivered
• traffic_qos.cc — NS-3 scenario with 3-flow SetupApplications + Tos/DSCP
• flow_metrics.py — Control PDR, P99 latency, throughput share, PASS/CHECK vs targets
• CMakeLists.txt target traffic-qos · sample NR runs at 5/10/15 STA
• traffic_qos_report.pdf — still pending (needs full 192-run matrix for proper report)
Robot NW Connection Simulator · July 2026 Progress
3 / 8

## Slide 4
RELIABILITY
WiFi BSSID crash — root cause & fix
What crashed
NS_ASSERT in sta-wifi-mac.cc:1392
GetLink(linkId).bssid == hdr.GetAddr3()
During multi-AP roaming (4 APs, same SSID MeshHotspot):
1. STA associates toward AP 0c
2. MissedBeacons → abandon → re-assoc to AP 0b
3. Delayed AssocResp from abandoned AP 0c arrives
4. Assert: stored BSSID=0b ≠ response BSSID=0c → abort
Not a scenario bug — ns-3.45 over-strict invariant under heavy roaming.
Fix & verification
Patch in ReceiveAssocResp:
Ignore AssocResp whose BSSID ≠ current link target.
Keep waiting for the AP we are currently associating with.
Before (sweep): 4 / 9 runs crashed
After (sweep): 9 / 9 runs completed
Verified on previously-failing cases:
• seed 6 / STA 5 · seed 6 / STA 10
• seed 7 / STA 15 · seed 8 / STA 15
All now finish full 60 s without NS_ASSERT.
Robot NW Connection Simulator · July 2026 Progress
4 / 8

## Slide 5
SWITCH RECOVERY
Path recovery logic — toward ~80% resolved
A switch was often marked timeout because recovery was measured on Sensor TCP (RTO/slow-start), not true path recovery. Return Cellular → WiFi was stranded by head-of-line pending events.
BEFORE (seed 7 · 10 STA · NR)
57%
resolved switches
20/47
timeout events
AFTER A+B (same seed / STA)
87%
resolved switches
2/47
timeout events
What changed (A + B)
A. Control-UDP liveness — resolve switches on continuous 50 ms Control RX (true Cellular↔WiFi path recovery), not Sensor TCP RTO.
B. Head-of-line fix — stale pending switches retired as superseded when a newer path decision is made (no stranded FIFO).
Full 9-run matrix aggregate: 73% resolved · 15% timeout · 12% superseded (seed-dependent; see next slide).
Robot NW Connection Simulator · July 2026 Progress
5 / 8

## Slide 6
EVALUATION MATRIX
How seeds & STA counts differ (NR, 60 s)
Seed | STA | Switches | Resolved | Timeout | Timeout % | Median ms
6 | 5 | 24 | 14 | 6 | 25% | 65
6 | 10 | 60 | 42 | 8 | 13% | 61
6 | 15 | 96 | 72 | 16 | 17% | 245
7 | 5 | 23 | 15 | 4 | 17% | 564
7 | 10 | 47 | 41 | 2 | 4% | 55
7 | 15 | 84 | 62 | 13 | 15% | 63
8 | 5 | 34 | 29 | 2 | 6% | 39
8 | 10 | 60 | 50 | 6 | 10% | 52
8 | 15 | 78 | 45 | 18 | 23% | 557
Key insight
Best case
seed 7 / STA 10 → 4% timeout, median 55 ms
Worst cases
seed 6 / STA 5 → 25%
seed 8 / STA 15 → 23%
Takeaway
A single seed would have overstated reliability. Multi-seed + multi-STA is required for the report.
Aggregate: 506 switches · 73% resolved
Robot NW Connection Simulator · July 2026 Progress
6 / 8

## Slide 7
JULY PLAN ALIGNMENT
Enhancement plan checklist
July item (plan) | Status | Evidence
traffic_qos.cc — 3-flow model | DONE | Control/Sensor/Video + DSCP Tos
flow_metrics.py — per-flow KPIs | DONE | PDR, P99, tput share, PASS/CHECK
Control PDR & P99 analysis | PARTIAL | Scripts ready; needs full matrix
traffic_qos_report.pdf | PENDING | Requires 192-run campaign
BSSID crash (blocker) | FIXED | 9/9 sweep completes
Switch recovery (A+B) | DONE | 57% → 87% on seed7/STA10
July alignment verdict
Core July implementation is in place (code + measurement). The formal analysis report is the remaining gap — blocked only by scale of evaluation, not by missing software units.
Robot NW Connection Simulator · July 2026 Progress
7 / 8

## Slide 8
NEXT STEP
192-run campaign for a proper report
The enhancement plan’s comparison matrix is 192 scenarios. A proper traffic_qos_report.pdf needs that full campaign — not single-seed anecdotes.
What 192 covers
• Cellular mode: LTE vs NR
• STA counts: 5 / 10 / 15
• Seeds: 6 / 7 / 8 (× more later)
• Mobility: waypoint + baseline
• Traffic: Control/Sensor/Video QoS
• Enable/disable switching baselines
Automation plan
• run_seeds / sweep script
• Parallel batch execution
• Per-run FlowMonitor + switch log
• flow_metrics.py aggregation
• Bootstrap CI + Mann-Whitney later
• Markdown → PDF report pipeline
Report outputs
• Control PDR & P99 tables
• Per-flow throughput share
• Switch timeout / interruption
• LTE vs NR comparison
• Seed-averaged KPIs ± CI
• traffic_qos_report.pdf
Goal: execute the 192-run matrix → aggregate KPIs → publish traffic_qos_report.pdf as the July analysis deliverable (then expand toward 10-seed / 640 for Sep statistics).
Robot NW Connection Simulator · July 2026 Progress
8 / 8