## Slide 1: NS-3 Simulation Enhancement — Progress Update
Phase 1 Supplementary Plan: Four Accuracy Improvements
Hybrid Network for Multi-Robot Construction Sites
PIC Lab, KIT | Reporting period: current

## Slide 2: What the Enhancement Plan Covers
Goal: reduce the gap between simulation and field validation before Phase 2 / Phase 3.
Item 1 — Realistic mobility: replace random Gauss-Markov with Waypoint + dwell-time routes.
Item 2 — Traffic model: separate control, sensor, and video flows with per-flow QoS metrics.
Item 3 — WiFi mesh internal handover: model intra-mesh AP changes and a guard timer.
Item 4 — Statistical reinforcement: more seeds, confidence intervals, significance tests.

## Slide 3: Current Progress by Item
Enhancement item | Target | Status | Done so far
1. Realistic mobility (Waypoint) | Jun 2026 | In design | Requirements reviewed; route types and dwell model defined
2. Traffic QoS separation | Jul 2026 | Scoped | Flow types and QoS thresholds identified
3. WiFi mesh internal HO | Aug 2026 | Planned | Event classification scheme drafted
4. Statistical reinforcement | Sep 2026 | Planned | Seed-count and test methods selected
Status reflects early-stage work: requirements analysis and design decisions completed; implementation begins with Item 1.

## Slide 4: Progress Completed This Period
Analyzed the four enhancement items and mapped each to the field-validation risk it addresses.
Defined the Waypoint mobility design: patrol loops, path movement, work stops, obstacle approach.
Selected speed levels for comparison: 0.5, 2.0, and 5.0 m/s against the Gauss-Markov baseline.
Drafted the switching-event classification (intra_mesh / wifi_to_cell / cell_to_wifi) for the new log.
Confirmed the statistics plan: 10 seeds, bootstrap 95% CIs, Mann-Whitney U and Kruskal-Wallis tests.

## Slide 5: Immediate Next Steps
Next step | Item | Expected output
Implement Waypoint mobility scenarios | 1 | waypoint_mobility.cc + 3 scenario JSON files
Produce first visualization drafts | 1 | 3D trajectory plot, RSSI heatmap
Prototype per-flow QoS traffic split | 2 | traffic_qos.cc skeleton
Set up multi-seed run automation | 4 | run_seeds.sh draft
Thank You
Questions & Discussion